INFO-I 492 Senior Thesis

Project Status Report #04

Week 7

| Student | Gabriel Long |
| --- | --- |
| Course | INFO-I 492 Senior Thesis |
| Instructor | Dr. Sridhar Ramachandran |
| Report | Project Status Report 04 |

Indiana University Indianapolis

# Original Plan for This Week

Complete the Week 7 synthesis milestone in `docs/project_plan.md` and prepare direct handoff into the Week 8 draft milestone in `docs/manuscript_skeleton.md`.

Finalize the held-out candidate comparison table using the four candidate metric files in `outputs/metrics` and align selection logic to `model_selection_framework.md`.

Consolidate robustness and governance evidence for reporting readiness using `outputs/tables/multiseed_stability_seed2026_2029.csv`, `outputs/tables/heldout_bootstrap_ci_seed2026.csv`, `outputs/tables/hgb_hyperparameter_sensitivity_seed2026.csv`, `outputs/tables/subgroup_performance_seed2026.csv`, and `outputs/tables/hgb_seed2026_full_perm_importance_summary_extended.csv`.

Formalize Week 7 decision and documentation artifacts in `docs/status_reports/report_04/week07_model_selection_decision.md`, `docs/status_reports/report_04/week07_run_manifest.json`, and `docs/status_reports/report_04/week07_docs_audit.md`.

Preserve frozen protocol continuity by confirming additive-only reporting changes and rerunning `scripts/13_upgrade_integrity_check.py`.

# Tasks Accomplished This Week

Consolidated held-out candidate model performance from existing artifacts in `outputs/metrics/metrics_test_seed2026_hgb_full_none.csv`, `outputs/metrics/metrics_test_seed2026_hgb_full_platt.csv`, `outputs/metrics/metrics_test_seed2026_hgb_full_isotonic.csv`, and `outputs/metrics/metrics_test_seed2026_logreg_full_none.csv`.

Completed and preserved model selection decision formalization in `docs/status_reports/report_04/week07_model_selection_decision.md` using criteria documented in `model_selection_framework.md`.

Reviewed and connected prior Week 6 comparative evidence from `outputs/tables/week06_full_feature_comparison_seed2026.csv`, `outputs/tables/week06_bullying_ablation_comparison_seed2026.csv`, and `outputs/tables/week06_calibration_sensitivity_seed2026.csv` to the Week 7 narrative.

Completed Week 7 documentation coherence package in `docs/status_reports/report_04/week07_alignment_with_feedback.md`, `docs/status_reports/report_04/week07_docs_audit.md`, and `docs/status_reports/report_04/week07_run_manifest.json`.

Updated Week 8 drafting scaffolds in `docs/manuscript_skeleton.md` and `docs/figures_tables_inventory.md` with explicit table and figure insertion targets.

Confirmed that Week 7 remained a synthesis and decision formalization week with scope protection and evidence traceability.

## Held-Out Candidate Model Comparison (Seed 2026)

| Candidate model | ROC AUC | PR AUC | Brier | Calibration slope | Calibration intercept | Abs(slope - 1) | Source |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HGB full + Platt | 0.716057 | 0.644073 | 0.206122 | 1.005455 | 0.014371 | 0.005455 | `outputs/metrics/metrics_test_seed2026_hgb_full_platt.csv` |
| HGB full none | 0.716057 | 0.644073 | 0.206178 | 1.046301 | 0.027978 | 0.046301 | `outputs/metrics/metrics_test_seed2026_hgb_full_none.csv` |
| HGB full + isotonic | 0.713738 | 0.618789 | 0.206546 | 0.980255 | -0.000656 | 0.019745 | `outputs/metrics/metrics_test_seed2026_hgb_full_isotonic.csv` |
| Logreg full none | 0.715534 | 0.643474 | 0.212558 | 0.974171 | -0.368623 | 0.025829 | `outputs/metrics/metrics_test_seed2026_logreg_full_none.csv` |

The candidate table supports the Week 7 selection lock because `hgb_full_platt` has the lowest held-out Brier and the closest slope to 1 under the documented ranking order.

The comparison confirms that calibration choice changed probability quality more than ranking quality for the HGB family under this seed and split.

The logistic reference remained competitive on ROC AUC but stayed weaker on Brier and intercept, which supported its role as baseline context rather than final selection.

Quality control checks completed:

`outputs/audits/week07_upgrade_integrity_audit.md` confirmed frozen protocol continuity and additive-only Week 7 reporting updates.

Backtick-path existence checks passed for `docs/status_reports/report_04/Project_Status_Report_04_Submission.md`, `docs/status_reports/report_04/week07_model_selection_decision.md`, and `docs/status_reports/report_04/week07_alignment_with_feedback.md`.

DOCX structure and style checks confirmed required headings plus role tables with `Light Shading Accent 1` formatting in `docs/status_reports/report_04/Project_Status_Report_04_Submission.docx`.

# Comparison of Planned vs Actual

| Planned Week 7 task | Actual completion and evidence |
| --- | --- |
| Finalize model selection under fixed held-out criteria | Completed through criteria-ordered candidate review in `docs/status_reports/report_04/week07_model_selection_decision.md` with held-out inputs from `outputs/metrics`. |
| Consolidate robustness and governance evidence for final reporting | Completed with descriptive summaries tied to `outputs/tables/multiseed_stability_seed2026_2029.csv`, `outputs/tables/heldout_bootstrap_ci_seed2026.csv`, `outputs/tables/hgb_hyperparameter_sensitivity_seed2026.csv`, `outputs/tables/subgroup_performance_seed2026.csv`, `outputs/tables/hgb_seed2026_full_perm_importance_summary_extended.csv`, and `outputs/audits/week07_upgrade_integrity_audit.md`. |
| Package Week 7 report artifacts with clear evidence traceability | Completed in `docs/status_reports/report_04/Project_Status_Report_04_Submission.md`, `docs/status_reports/report_04/week07_model_selection_decision.md`, `docs/status_reports/report_04/week07_alignment_with_feedback.md`, `docs/status_reports/report_04/week07_docs_audit.md`, and `docs/status_reports/report_04/week07_run_manifest.json`. |
| Preserve frozen protocol assets | Completed with additive-only reporting work and continuity confirmation in `outputs/audits/week07_upgrade_integrity_audit.md` and `docs/status_reports/report_03/week06_context.json`. |

This week shifted from planned additional figure generation to stronger evidence consolidation once existing Week 6 and Week 7 artifacts were confirmed complete. The adjustment occurred because duplicate figure production would not improve the argument quality and would reduce drafting bandwidth. The updated scope improved coherence by linking model selection, robustness, governance, and documentation actions into one traceable chain. This adjustment improved Week 8 readiness by reducing unresolved reporting choices and by stabilizing the manuscript input package.

# Self-Rating of Progress

☑ Met the Planned Tasks

☐ Did Not Meet the Planned Tasks

Rationale:

Week 7 synthesis objectives were completed with complete evidence traceability and frozen protocol continuity.

The report package now links decision logic, robustness evidence, and governance checks through concrete repository artifacts.

Voice reflection:

Week 7 confirmed that the primary bottleneck is synthesis quality rather than additional metric generation. The highest value work was converting many valid outputs into a coherent and defensible narrative with explicit evidence paths. New modeling runs were intentionally deferred because required Week 7 artifacts already existed and additional runs would have increased scope risk without clear reporting gain. That decision reduced timeline risk for Week 8 and prevented avoidable protocol branching during draft preparation. The completed package now supports faster manuscript drafting with fewer unresolved decisions about model choice, robustness framing, and documentation mapping. This positions Week 8 work to focus on writing quality, section integration, and final argument clarity.

# Plan for Next Week

Replace Methods placeholders in `docs/manuscript_skeleton.md` with complete draft text for data source, outcome definition, predictors, split protocol, metrics, and calibration approach.

Draft Results narrative in `docs/manuscript_skeleton.md` using the candidate comparison table and decision memo from `docs/status_reports/report_04/week07_model_selection_decision.md`.

Align all table and figure references in manuscript text to `docs/figures_tables_inventory.md` and confirm one to one correspondence.

Draft the limitations and ethics subsection in `docs/manuscript_skeleton.md` using `deployment_and_use_constraints.md`, `risk_register.md`, and `model_selection_framework.md` as source constraints.

Run documentation coherence checks before Week 8 submission updates by reviewing `docs/experiment_log.md`, `docs/decisions_log.md`, and `docs/status_reports/report_04/week07_docs_audit.md`.

Regenerate existing artifacts only if a specific missing file is detected during draft integration, then record that regeneration in `docs/experiment_log.md`.

# Evidence of Tasks Completed

Evidence access note: project documentation does not include a public repository URL. Reviewer navigation for committed evidence locations is documented in `README.md` under `Navigation for Reviewers`, and the report evidence paths are listed below.

| Category | Evidence Artifacts |
| --- | --- |
| Planning and governance docs | README.md docs/project_plan.md docs/analysis_plan.md model_selection_framework.md deployment_and_use_constraints.md risk_register.md qa_checklist.md |
| Held-out candidate metrics | outputs/metrics/metrics_test_seed2026_hgb_full_none.csv outputs/metrics/metrics_test_seed2026_hgb_full_platt.csv outputs/metrics/metrics_test_seed2026_hgb_full_isotonic.csv outputs/metrics/metrics_test_seed2026_logreg_full_none.csv |
| Week 6 and Week 7 tables | outputs/tables/week06_full_feature_comparison_seed2026.csv outputs/tables/week06_bullying_ablation_comparison_seed2026.csv outputs/tables/week06_calibration_sensitivity_seed2026.csv outputs/tables/multiseed_stability_seed2026_2029.csv outputs/tables/heldout_bootstrap_ci_seed2026.csv outputs/tables/hgb_hyperparameter_sensitivity_seed2026.csv outputs/tables/subgroup_performance_seed2026.csv outputs/tables/hgb_seed2026_full_perm_importance_summary_extended.csv |
| Integrity and continuity | outputs/audits/week07_upgrade_integrity_audit.md docs/status_reports/report_03/week06_context.json docs/status_reports/report_03/week06_run_manifest.json |
| Week 7 reporting package | docs/status_reports/report_04/week07_model_selection_decision.md docs/status_reports/report_04/week07_alignment_with_feedback.md docs/status_reports/report_04/week07_docs_audit.md docs/status_reports/report_04/week07_run_manifest.json |
| Drafting and project logs | docs/experiment_log.md docs/decisions_log.md docs/manuscript_skeleton.md docs/figures_tables_inventory.md |